## Resource 1 - Charts & Calcs
RESOURCE 1 ¦ Track A - Chart & Calc Engine Backlog
Fully independent: no pending decisions, no blockers. Can start on A1 today. Primary files: engine.py, calc_translator.py, tableau_parser.py (render/parse paths). Only hard dependency is A1 -> A2. Full context: HANDOFF_TRACK_A_CHART_CALC.md
ID | Task | Priority | Est (days) | Depends on (task) | Dependency tier | Needs Sharath? | Local evidence / what unblocks it | Primary files | Done when | Status | Owner notes
A1 | Bins - numeric FLOOR binning: floor(field/binsize)*binsize. NOT the 'categorical-bin' user GROUPS already handled at tableau_parser.py:2017 - different construct, do not confuse. Top corpus gap: 197 occurrences. | P0 | 1.5 | - | 1 - INDEPENDENT | No | Corpus workbooks with bins are local in Workbooks/. Regression suite runs fully offline (DuckDB + fake Snowflake sessions) - verified by a full 81-gate run with no credentials. | tableau_parser.py, calc_translator.py, engine.py | A real corpus workbook using bins renders with numerically correct bucket boundaries, locked by a new gate in tests/test_regression.py. | Not started | START HERE - no blockers
A2 | Histogram - bar chart over a binned continuous measure with COUNT/COUNTD aggregate. New r_histogram in engine.py, dispatched off A1's bin detection. | P0 | 1 | A1 | 1 - INDEPENDENT | No | Local. Only dependency is task A1. | engine.py | Histogram sheet renders with correct bucket counts vs a hand-computed reference. | Not started | Blocked until A1 lands
A3 | Table calcs RUNNING_*/LOOKUP/TOTAL/FIRST/LAST. Currently in the refusal regex at calc_translator.py:118. Needs the sheet's own sort context fed into a window ORDER BY. Read how RANK/RANK_DENSE/RANK_UNIQUE were done (calc_translator.py:240-280) first - same family. | P1 | 2 | - | 1 - INDEPENDENT | No | Local corpus workbook + DuckDB. No account needed. | calc_translator.py, engine.py | A RUNNING_SUM or LOOKUP calc against a real corpus workbook matches Tableau's own displayed running total exactly. | Not started
A4 | Native Measure Names/Values selector. The calc-based form (a CASE calc on a parameter) is ALREADY DONE and numerically verified on Superstore_TopN_MeasureSwap. Only Tableau's native no-calc shelf construct is missing - the parameter is already captured, the switch-wiring is the gap. | P1 | 1 | - | 1 - INDEPENDENT | No | Superstore_TopN_MeasureSwap.twbx is local at the repo root, and superstore_topn_measureswap_ir.json is already parsed. | tableau_parser.py, engine.py | A workbook using the native selector renders and switches measures correctly, routed through the same path the calc-based form already uses. | Not started
A5 | Box-whisker chart. New r_boxwhisker in engine.py. Altair has native mark_boxplot() - verify Tableau's quartile method and outlier display match Altair's defaults before assuming a 1:1 mapping. | P2 | 1 | - | 1 - INDEPENDENT | No | Local. | engine.py | Min/Q1/median/Q3/max match a hand-computed reference on a test workbook. | Not started
A6 | Bullet chart. New r_bullet in engine.py. Needs qualitative-range bands + target marker. Reference-line parsing (_refline_rule, engine.py:981) is structurally similar to a bullet's target - read it first. | P2 | 1 | - | 1 - INDEPENDENT | No | Local. | engine.py | Bands and target marker render correctly against a test workbook. | Not started
A7 | True matrix / pivot table - row+column dimension crossing with subtotals. DISTINCT from the existing flat crosstab (r_table / _rank_table). | P2 | 2 | - | 1 - INDEPENDENT | No | Local. | engine.py | Read _rank_table (engine.py:1802) and r_table fully BEFORE starting - a naive implementation duplicates a lot of existing formatting/glyph logic. | Not started | Most structurally different item
A8 | Map/choropleth blank-in-sandbox fallback. Plotly-rendered maps are known to render blank inside the SiS sandbox (a platform limit, not a parsing bug). Needs a bar/table fallback presentation. | P2 | 1 | - | 1 - INDEPENDENT | No - has Snowflake | Needs the Streamlit-in-Snowflake sandbox to verify the blank-map behavior and prove the fallback (cannot be reproduced locally - the blank map IS a sandbox-only platform limit). CONFIRMED 2026-08-13: the resource has Snowflake/Snowsight access, so this is theirs to do. Needs the connections.toml entry for wb19670-c2gpartners. | engine.py | Fallback renders with an honest finding stating why - never a silent blank. | Not started
A9 | Rich hover tooltips - custom tooltip fidelity (155x in corpus, cosmetic). | P3 | 1 | D3 | 2 - ONE-TIME UNBLOCK | Decision D3 | Work itself is fully local. Only needs you to confirm it is still deprioritized before the resource spends a day on it. | engine.py | CONFIRM WITH SHARATH still deprioritized before starting - status_config.json records this as user-deprioritized. | Not started | Confirm priority first
A10 | Pixel-exact layout cosmetics - hollow scatter marks, reference-line labels, narrow-column truncation. | P3 | 1 | - | 1 - INDEPENDENT | No | Local. | engine.py | Visual parity on the named cosmetic cases. Lowest priority - take last. | Not started
| TOTAL (estimated days) |  |  |  |  | days independent |  |  | All 10 items estimated from MVP_ACCELERATOR_SCOPE.md's own tracked figures.

## Resource 2 - Validation
RESOURCE 2 ¦ Track B - Validation & Data-Model Correctness
UPDATED 2026-08-13: D1/D2 decided, so B1/B2/B6/B7/B8 are ALL unblocked - start on any of them. Only B3/B4 still wait on the E1/E2 crosstab exports, and B5 needs Snowflake. Primary files: validation_report.py, validation_adapter.py, deep_validation.py, app_screenshot.py. Full context (incl. the D1/D2 rationale): HANDOFF_TRACK_B_VALIDATION.md
ID | Task | Priority | Est (days) | Depends on (task) | Dependency tier | Needs Sharath? | Local evidence / what unblocks it | Primary files | Done when | Status | Owner notes
B1 | order_match chart-level FAIL semantics (validation_report.py:198, made a structural_failure at line 206). Live on Regional Analysis, TWO fully-evidenced charts read chart-level FAIL while EVERY individual cell passes - purely from row sequence. DECIDED: implement as a structural FAIL only for ranked/top-N charts; informational flag everywhere else. | P0 | not est. | - | 1 - INDEPENDENT | No - D1 DECIDED | UNBLOCKED 2026-08-13. Sharath's ruling: order is a structural FAIL only for ranked/top-N charts; informational elsewhere. Work is fully offline (validation_report.py + local fixtures). Full rationale in HANDOFF_TRACK_B_VALIDATION.md item 1. | validation_report.py | Gate proves BOTH sides: a ranked list STILL fails on wrong order, a grouped bar chart no longer does. DO NOT simply delete the check, and do NOT weaken it for ranked lists - it touches the vendored engine's structural-failure semantics. | Ready | D1 decided 2026-08-13
B2 | Global Sales Dashboard View2 crash. Crashed the then-current capture during the 2026-08-11/12 screenshot testing and was NEVER root-caused - the session moved to the real-screenshot rewrite first. An earlier status-doc draft wrongly claimed this workbook was tested and fixed; it was not. | P0 | not est. | - | 1 - INDEPENDENT | No | Globalsalesdashboard.twbx IS present in Workbooks/ and globalsalesdashboard_ir.json is already parsed. Reproduces locally with app_screenshot.py against a locally-run app - no SSO, no account. | app_screenshot.py, deep_validation.py, headless_render.py | FIRST question to answer: does it still reproduce under app_screenshot.capture_app, or was it specific to the now-retired headless_render image path? That answer decides whether this is a live bug or already moot. Either fixed, or proven moot with evidence. | Not started | START HERE - needs no decision. 3rd corpus workbook = highest-value generalization proof
B3 | Pivoted / long-shape Tableau crosstab alignment. Tableau's REST crosstab sometimes returns a long shape (Measure Names / Measure Values columns) instead of wide, so those charts lose their Tableau leg entirely. | P1 | not est. | - | 2 - ONE-TIME UNBLOCK | ONE sample CSV | BLOCKER CONFIRMED: no saved live Tableau crosstab exists anywhere in the repo, and there is NO fixture for the pivoted Measure Names/Measure Values shape (checked tests/fixtures/ and every reports/ pack). Export ONE crosstab in that shape and this goes fully offline. | validation_adapter.py, deep_validation.py | Reshape works AND _assign_dashboard_csv_by_header (deep_validation.py:96) still resolves uniquely afterward. CAREFUL: the exact-header-set matcher was chosen over a subset match because subset matching was proven genuinely ambiguous against live data - reshaping changes the header set it sees. | Not started
B4 | Date-part column-name aliasing. Date-part-grouped Tableau headers (e.g. 'Month of Order Date') don't alias to the chart's own 'Order Date' grain, so those columns never compare. | P1 | not est. | - | 2 - ONE-TIME UNBLOCK | ONE sample CSV | Same as B3 - needs one crosstab whose header carries a date-part grouping (e.g. 'Month of Order Date'). None saved locally. | validation_adapter.py, parity.py | Verified against a REAL pulled crosstab, not an assumed header format. Related machinery: parity._sheet_pill_captions and engine._part_num (engine.py:583). | Not started
B5 | Two unresolved backend measures - 'Days to Ship Scheduled' and 'Sales Forecast' don't resolve against the backend table, so their charts can't complete the backend leg. | P1 | not est. | - | 1 - INDEPENDENT | No - has Snowflake | Needs the real backend table to diagnose which of three causes applies (calc gap / column-mapping gap / column genuinely absent) - cannot be determined from the workbook XML alone. CONFIRMED 2026-08-13: the resource has Snowflake/Snowsight access, so this is theirs. Needs the connections.toml entry for wb19670-c2gpartners. | validation_adapter.py, calc_translator.py | Diagnose which of three causes applies - calc-translation gap, column-mapping gap, or genuinely absent from the loaded table. Each has a very different fix. | Not started
B6 | Discount AVG-vs-SUM app bug. profile_superstore.py:20 curates 'Discount': AVG(DISCOUNT), which silently overrides the workbook's own declared agg=sum. Validation caught it and Tableau itself settled it via REST: Tableau 0.2/0.8/0.4, app 0.1/0.2/0.1, backend 0.2/0.8/0.4 - THE MIGRATED APP IS WRONG. | P1 | not est. | - | 1 - INDEPENDENT | No - D2 DECIDED | UNBLOCKED 2026-08-13. Sharath's ruling: respect the workbook's declared aggregation - a curated profile entry applies only where the workbook declares that same agg. Comparison numbers already proven live. Fix is local; DEPLOYING it later needs Snowflake, and it changes numbers the deployed app renders. See HANDOFF_TRACK_B_VALIDATION.md item 5b. | profile_superstore.py, engine.py (resolve_measure ~line 218-255) | DECIDED: respect the workbook's declared aggregation - a curated profile entry applies ONLY where the workbook declares that same agg, otherwise the workbook wins. This is the STRUCTURAL fix (kills the whole bug class), not a one-line swap to SUM. Done when Product Detail Sheet Discount matches Tableau's 0.2/0.8/0.4 AND sheets where AVG is correct still read AVG, gated both ways. Changes numbers the DEPLOYED app renders -> needs redeploy + tracker update. | Ready | D2 decided 2026-08-13
B7 | tableau_parser.source_tables() misreports a legacy-joined object. Its findall('.//relation[@type=table]') walks relations nested inside a legacy <relation type='join'> clause tree, so Globalsalesdashboard's single already-resolved object reports as a '3-table data model'. | P2 | not est. | - | 1 - INDEPENDENT | No | Pure XML parsing against Globalsalesdashboard.twbx, which is local. No runtime, no account, no data. | tableau_parser.py | Skip relations nested inside another relation's <clause> subtree. NOTE: practical impact today is NONE - the bindable=False outcome is already the correct conclusion; only the REASON STRING is misleading. | Not started | Reason-string only, no behavior change
B8 | Multi-fact / cyclic graph refusal - PROOF only, no fix expected. The refusal logic is BUILT (DATA_MODEL_STATUS.md 3.4/3.5) but has only ever been proven on synthetic fixtures. | P2 | not est. | - | 1 - INDEPENDENT | No | tests/make_datamodel_workbooks.py generates the workbook locally; the refusal path is offline logic. | tests/make_datamodel_workbooks.py, semantic_layer.py | Build a real workbook (two facts sharing one dim, or a 3-table loop) and confirm the refusal fires correctly on real XML. Expected outcome is a PASSING PROOF, not a code fix. | Not started
| TOTAL - deliberately NOT estimated |  | TBD | [5 empty] | DELIBERATELY NOT ESTIMATED: B2-B5 are investigate-then-fix, and no honest day figure exists yet. Resource 2's day-one deliverable is a real estimate for B2-B5, reported back before committing to a timeline.

## Decisions & Unassigned
DECISIONS - D1 and D2 DECIDED 2026-08-13
D1 and D2 are answered, which unblocked B1 and B6. Only the two crosstab exports (E1/E2) remain outstanding from Sharath. D3 is not blocking anyone.
ID | The question | SHARATH'S RULING | Status / notes | Task
D1 | order_match: should an exact row-ORDER mismatch fail a chart that is NOT a ranked list? Today it does - so on Regional Analysis two charts read chart-level FAIL while every single cell passes. | DECIDED 2026-08-13: order is a structural FAIL ONLY for charts where display order carries meaning (rank tables, top-N). Everywhere else it becomes an INFORMATIONAL flag. Do not delete the check; do not weaken it for ranked lists. The gate must prove BOTH directions. | DECIDED - B1 is unblocked and ready to build. Rationale is written into HANDOFF_TRACK_B_VALIDATION.md item 1. | B1 - READY
D2 | Discount = AVG or SUM? profile_superstore.py:20 curates AVG(DISCOUNT), overriding the workbook's declared agg=sum. Tableau's own REST values prove the app is wrong (app 0.1/0.2/0.1 vs Tableau 0.2/0.8/0.4; backend agrees with Tableau). | DECIDED 2026-08-13: respect the WORKBOOK's declared aggregation. A curated profile entry applies only where the workbook declares that same agg; otherwise the workbook wins. Structural fix, NOT a one-line swap to SUM - it closes the whole bug class rather than this one measure. | DECIDED - B6 is unblocked. NOTE: this changes numbers the DEPLOYED app renders, so it needs a redeploy + tracker update. See HANDOFF_TRACK_B_VALIDATION.md item 5b. | B6 - READY
D3 | Is the Track A backlog order still the priority you want? The list follows MVP_ACCELERATOR_SCOPE.md. Rich tooltips (A9) is recorded as 'user deprioritized'. | NOT formally answered - the MVP_ACCELERATOR_SCOPE.md order stands by default and A9 remains last. Confirm before anyone spends a day on A9. | Resource 1 is NOT blocked by this: A1 (Bins) was never gated on it. | A-track order
STILL OUTSTANDING FROM SHARATH - two file exports (~15 min), unblocks B3 + B4
ID | Export needed | Why it's blocking | How | Unblocks
E1 | One Tableau crosstab CSV in the PIVOTED / LONG shape (Measure Names / Measure Values columns). | CONFIRMED MISSING: no live Tableau crosstab CSV is saved anywhere in the repo, and there is no fixture for the pivoted shape at all (checked tests/fixtures/ and every reports/ pack). B3 cannot be worked offline without it. | Worksheet -> Export -> Data (or Download -> Crosstab -> CSV in Tableau Cloud/Server). Save into tests/fixtures/ and commit. | B3
E2 | One Tableau crosstab CSV whose header carries a DATE-PART grouping (e.g. 'Month of Order Date'). | Same situation as E1 - none saved locally. B4 needs a real header to align against, not an assumed format. | Same export path. Save into tests/fixtures/ and commit - both then become PERMANENT regression fixtures, not just a one-time unblock. | B4
NOT ASSIGNED TO EITHER RESOURCE - needs Snowsight access, not an engineer
ID | Task | Est | Suggested owner | Note
S1 | R9 UI upload confirmation - upload Workbooks/R9_Live_Join_Orders_Product_Category.twb through the deployed pipeline_demo app. Code-complete, gated, already verified against the real account via pipeline.onboard(). Same final UI confirmation R3 and R10 passed. | ~10 min, no dev work | DELEGATE to Resource 2 (they have Snowsight) | Closes the last open data-model verification item.
S2 | MVP sign-off (item #6) - your own visual confirmation in Snowsight. The last open MVP item; explicitly not dev work. | - | Sharath | MVP reads 5 of 6 done; this is the 6th.
S3 | Confirm R8 deploy status - the Cortex-vision re-wire was marked 'NOT YET DEPLOYED' on 2026-08-07, and ARCHITECTURE.md:1579 notes one such banner is itself stale. Needs a look at what is actually live. | ~15 min | Whoever has Snowsight access | Do this before anyone trusts either claim in the docs.
DEPENDENCY TIER LEGEND (the 'Dependency tier' column on both resource tabs)
1 - INDEPENDENT | Fully self-contained. Everything needed is already in the repo - the corpus workbooks live in Workbooks/, the parsed IR fixtures are committed, and the regression suite runs entirely offline on DuckDB + fake Snowflake sessions (verified 2026-08-13 by a full 81-gate run with NO credentials). Hand over the repo and the resource is productive immediately.
2 - ONE-TIME UNBLOCK | Needs ONE thing from you, once - then fully offline. Either a 2-minute decision (D1/D2/D3) or a single exported sample file. Total cost to you across all five tier-2 tasks is roughly 30 minutes, and it is the highest-leverage time you can spend on this handoff.
3 - NEEDS SNOWFLAKE | Genuinely needs your Snowflake / Snowsight account and cannot be delegated without credentials. NOTE: this is about DIAGNOSIS. Deploying any finished fix also needs Snowflake, but that batches - both resources build and gate-lock offline, and you deploy in a single pass.
SUMMARY (updated 2026-08-13, after D1/D2 were decided AND both resources were confirmed to have Snowflake/Snowsight access): 16 of 18 tasks are now tier 1 - zero dependency on Sharath. Resource 1: ALL 10 tasks independent (A8 included, since it only needed the Snowflake sandbox). Resource 2: B1/B2/B5/B6/B7/B8 all independent. ONLY B3 and B4 remain gated, on the E1/E2 crosstab exports - and even those become self-serve if Resource 2 is given Tableau access, since they could export the two crosstabs themselves. S1/S3 should now be DELEGATED, not kept by Sharath. BOTH RESOURCES CAN START IMMEDIATELY.
GROUND RULES - BOTH RESOURCES
- COLLISION RISK: both tracks can touch engine.py. Track A owns it for new chart renderers. Track B may need it for channel captions (engine.py does not set real Tableau captions as axis/tooltip titles - documented as the 'biggest lever' for validation; the 2026-08-11 pie-theta fix was exactly this). RULE: Track B does not edit engine.py without telling Track A first. A caption change also alters the shipped app's visuals, so it needs its own decision.
- NO VERSION CONTROL in this working directory. With two people editing, set up git first or partition file ownership manually - there is no branch isolation and no undo.
- Regression suite must stay green: run 'python tests/test_regression.py' from the repo root. Verified green 2026-08-13: 82 gates defined, 81 auto-run all passing, 1 deliberately manual (needs a live session).
- Every fix needs a gate with PROVEN TEETH - revert your fix and confirm the gate goes red.
- Update status_config.json + MVP_ACCELERATOR_SCOPE.md IN THE SAME CHANGE as the feature/fix, not as a follow-up. test_tracker_consistency enforces part of this.
- TRUST INVARIANT: BLOCKED (never measured) and FAIL (proven wrong) must never look the same. A missing proof cannot become a pass.
- TRUST INVARIANT: never guess. Where the code refuses - an ambiguous crosstab, an unresolvable column, a multi-fact graph - that refusal IS the feature. At least two refusals here exist because a looser version was tried and found genuinely ambiguous against live data.
- TRUST INVARIANT: nothing is silently dropped. Every unsupported construct produces a named finding, never a blank chart or a guessed number.