## Pending Items
Tableau → Streamlit-in-Snowflake Accelerator — Pending Items
Open work to take the accelerator from working POC (Superstore) to production. Status as of Jul 2026.
# | Action Item | Area | Assigned To | Target Date | Status
1 | Visual-parity verification harness (render engine charts to PNG, compare to Tableau) | Testing | Sharath | Jun 2026 | Done
2 | Calc translation engine: aggregates, ratios, COUNTD, FIXED LOD, IF/CASE, DATEDIFF, parameters | Calc Layer | Sharath | Jun 2026 | Done
3 | Chart inference for 'Automatic' marks + compound axes + small-multiples/facets | Visualization | Sharath | Jun 2026 | Done
4 | Dashboard layout from Tableau zone geometry; one Streamlit tab per dashboard | Visualization | Sharath | Jun 2026 | Done
5 | Extract & apply filter values (range / categorical subset / Top-N) per worksheet | Calc Layer | Sharath | Jul 2026 | Done
6 | Table calculations (RANK / INDEX / WINDOW_* / % of total) → SQL window functions | Calc Layer | TBD | Aug 2026 | Done
7 | Manual (drag) sort order + computed sort fidelity | Visualization | TBD | Aug 2026 | Done
8 | Number/format, font, colour-theme & title fidelity to match Tableau styling | Visualization | TBD | Aug 2026 | Done
9 | Second datasource support (joins / blends) — e.g. Commission Model on Sales Commission source | Data Layer | TBD | Aug 2026 | In Progress
10 | Reference / distribution / trend lines | Visualization | TBD | Sep 2026 | Done
11 | Parameters as interactive widgets; sheet swapping; dynamic zone visibility | Visualization | TBD | Sep 2026 | Done
12 | Dashboard actions (filter / highlight / URL navigation) | Visualization | TBD | Sep 2026 | Not Started
13 | Custom tooltips | Visualization | TBD | Sep 2026 | Not Started
14 | Images / Logos / Shapes | Visualization | TBD | Sep 2026 | Not Started
15 | Row-Level Security via Snowflake roles / row-access policies | Data Layer | TBD | Sep 2026 | Not Started
16 | Deploy to Streamlit-in-Snowflake + auth/RBAC + scheduled data refresh (Snowflake Tasks) | Deployment | TBD | Oct 2026 | Not Started
17 | Accelerator UI: upload .twbx, pick dashboards, map data, one-click generate & deploy | Framework | TBD | Oct 2026 | Not Started
18 | QC report: data-to-data + visual comparison; flag complex charts not auto-converted with suggested chart type | Testing | TBD | Oct 2026 | Not Started

## Overall Effort
Overall Effort — by Stage
End-to-end build of the Tableau→Streamlit-in-Snowflake accelerator. Effort in person-days; P1 = highest priority.
# | Stage | Activity | Effort (days) | Priority | Status
1 | Discovery | Identify licenses (Snowflake, Streamlit-in-Snowflake), target architecture & warehouse/compute sizing | 5 |  | Done
|  | Inventory all Tableau workbooks/dashboards into a hierarchical Excel (source for migration tracking) | 2 | P1
2 | Data Layer (Snowflake) | Map Tableau datasources → Snowflake tables/views (the 'semantic model') | 8 | P1 | In Progress
|  | Custom SQL & Published datasources → Snowflake views | 5 | P3
|  | Load file-hosted sources (Excel/CSV) into Snowflake tables | 3 | P2 | Done
|  | Joins + relationships modelled in Snowflake; combination of both | 5 | P4
|  | Multiple datasources / data blending across sources | 5 | P6 | Not Started
|  | Calculated fields → Snowflake SQL (calc-translation engine: agg, ratio, COUNTD, IF/CASE, LOD) | 8 | P1 | Done
|  | Complex calcs — LOD, YTD/MTD, Sets, Groups, Hierarchies | 8 | P3 | In Progress
|  | Table calcs — RANK / INDEX / WINDOW_* / % of total → SQL window functions | 8 | P2 | In Progress
|  | Data prep — type conversion, alias, split/merge → pushed to Snowflake SQL | 6 | P5
|  | Row-Level Security via Snowflake roles / row-access policies | 5 | P4 | Not Started
|  | Live query (Snowpark) vs cached testing; multi-connection validation | 3 | P7
|  | Automate Snowflake data refresh / scheduling (Tasks, Dynamic Tables) | 3 | P8
3 | Rationalization | Rationalise semantic models; stale-content management | 6 |  | Not Started
|  | Push remaining data prep to the warehouse (BI → DB) | 4 |  | Not Started
4 | Visualization (Streamlit) | Core chart library — KPI, bar, line, area, scatter, highlight-table, map, text table | 15 | P1 | Done
|  | Compound axes + small-multiples / faceting; multi-dashboard tabs | 6 | P1 | Done
|  | Dashboard layout from Tableau zone geometry | 4 | P1 | Done
|  | Filters / slicers — single & multi-select, apply to one or more sheets | 6 | P2 | In Progress
|  | Formatting — colour theme, fonts, axis labels, number formats, titles, backgrounds | 10 | P3 | In Progress
|  | Parameters / sheet swapping / dynamic zone visibility | 6 | P5 | Not Started
|  | Dashboard actions & navigations (filter, highlight, URL) | 5 | P6 | Not Started
|  | Complex visuals — Sankey, matrix w/ conditional formatting, gantt, dual-axis | 12 | P7 | Not Started
|  | Images / Logos / Shapes | 3 | P8 | Not Started
|  | Flag Tableau extensions (TabPy etc.) with no SiS equivalent | 3 | P9 | Not Started
5 | App & Server | Deploy to Streamlit-in-Snowflake; auth / RBAC | 6 | P2 | Not Started
|  | Subscriptions, alerts, bookmarks / saved state equivalents | 5 | P5 | Not Started
6 | Testing | Sheet-level data-to-data comparison (UAT: row & aggregate) | 6 | P1 | In Progress
|  | Visual-parity check via render-to-PNG harness vs Tableau screenshots | 5 | P1 | Done
|  | QC report — data + visual diff; suggest chart type for unconverted complex charts | 5 | P3 | Not Started
7 | End-to-End Framework | Wrap parse → translate → codegen → deploy into one pipeline + UI | 10 | P1 | In Progress
|  | Accelerator UI (upload, map, generate, deploy); list dashboards that failed migration | 10 | P2 | Not Started
TOTAL EFFORT

## Future Vision
Future Vision
Where this accelerator goes beyond the first workbook.
▶ | Point the accelerator at ANY Tableau (or Power BI) environment: read the data model and publish it as a governed semantic layer directly in Snowflake.
▶ | Convert dashboards into Snowflake-native apps (Streamlit-in-Snowflake); keep the same engine portable to Databricks where needed.
▶ | Build an inference / analytics (AI + LLM) layer on top of the converted semantic layer — natural-language Q&A over the migrated dashboards.
▶ | Validate across multiple clients and cross-border scenarios: data residency, RLS, and per-region semantic differences.
▶ | When source tables are absent, map metrics from rationalised tables — maintained via a living mapping document.
▶ | Anticipate data-modelling changes per scenario: joins vs relationships, blends, live vs cached, incremental refresh.
▶ | LLM-assisted calc translation and chart-type recommendation for complex / unsupported Tableau visuals (the QC report closes the loop with the developer).

## Plan
Implementation Plan — indicative timeline
Phased delivery. Bars are indicative; sequence matters more than exact weeks. Team roles are placeholders.
Phase / Workstream | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Discovery (Lead + Data) | bar: Jul W1
Data Layer in Snowflake (Data Eng) | bar: Jul W1 to Aug W2
└ Calc & table-calc translation (Data Eng) | bar: Jul W2 to Aug W2
Rationalization (Data + Lead) | bar: Aug W1 to Aug W3
Visualization (Streamlit engine) (Viz Eng) | bar: Jul W2 to Sep W2
App & Server (SiS deploy, auth, refresh) (App Eng) | bar: Aug W4 to Sep W3
Testing (data UAT + visual parity) (QA) | bar: Jul W4 to Oct W1
End-to-End Framework + UI (All) | bar: Sep W1 to Oct W2
Team (placeholder — fill in)
Project Lead
Data Engineer (Snowflake)
Visualization Engineer
App / Deployment Engineer
QA / Testing
Indicative total ≈ 14 weeks; effort detailed in 'Overall Effort' tab.
Status legend (other tabs): | Jul W1: Done; Jul W3: In Progress; Aug W1: Not Started; Aug W3: Blocked