## Progress Tracker
Tableau → Streamlit-in-Snowflake Accelerator — Overall Progress Tracker
Generic capability coverage vs Tableau's full feature surface. Update % / RAG / Notes each cycle; overall rolls up. Blue = you edit.
Reporting date | 2026-07-15 | Overall coverage
# | Workstream | % Complete | RAG | Notes / status
1 | Workbook parsing & extraction | 92% | G | Parses any .twb/.twbx: all dashboards, sheets, zones, encodings, calcs, filters, sorts, number formats, colour scales, titles, Measure-Names. Only custom tooltips un-extracted on the 21-sheet reference workbook.
2 | Chart-type library | 80% | G | 10 core types render: KPI, bar, multi-measure bar, line, area, scatter, dot, highlight table, map, text table. Missing: matrix w/ conditional format, Sankey, gantt, dual-axis.
3 | Calculation translation (Tableau → Snowflake SQL) | 97% | G | Aggregates, ratios, COUNTD, FIXED LOD, IF/CASE, parameters translate. Table calcs (RANK/INDEX/WINDOW) parsed; engine wiring in progress. Some calcs (e.g. DATEDIFF) not yet translated — those sheets don't render.
4 | Data layer & connectivity | 75% | G | Runs on Snowflake (Snowpark) or locally (DuckDB); loads any table/column. Multi-datasource joins/blends and Row-Level Security not yet.
5 | Interactivity | 55% | A | Per-dashboard filters (single-select + date range) work. Parameters, sheet-swapping, dashboard actions, custom tooltips pending.
6 | Formatting & layout fidelity | 70% | G | Dashboard layout rebuilt from Tableau zone geometry; number formats, colour scales, sorts, titles applied. Full theme/fonts and images/logos/shapes pending.
7 | Deployment & operations | 80% | G | Publish-to-Streamlit-in-Snowflake, auth/RBAC, scheduled refresh, subscriptions/alerts not started.
8 | Quality & tooling | 90% | G | Two QA harnesses live: visual-parity (chart→image vs Tableau) and coverage-audit (flags un-converted constructs). Accelerator UI + automated QC report pending.
Completed this period |  |  | Planned next period
• Table-calc engine: WINDOW_*/RANK/INDEX → SQL windows; layered hoist for FIXED-in-agg chains. |  |  | • Bins + histogram; context filters (order of operations).
• Relationship flatten: multi-table extracts join automatically (E-Commerce 46→68%). |  |  | • Live-connection semantic views (non-extract joins/blends).
• Top-N filters (field + parameter), hierarchies drill selector, device layouts. |  |  | • Credentialed Snowflake deploy dry-run (write_pandas).
• 2024.3 sample pack: two official workbooks at 96%/100%; corpus now 7. |  |  | • Edge-case workbook for joins/multi-fact/RLS/parameter actions.
• Silent gaps closed: custom SQL, relative-date filters, log/reversed axes all report.
Risks & decisions needed
Item | Impact | Owner | Need by | Status
Multi-datasource & Row-Level Security need a Snowflake account + roles decision | Blocks data layer & deployment | Sharath | Aug 2026 | Open
Complex visuals (Sankey / matrix / dual-axis): auto-convert vs flag in QC report? | Scope & timeline | Sharath | Jul 2026 | Open
Effectively 1 developer today — plan assumes added data + app engineers | Timeline | Sharath | Jul 2026 | Open
Agree the 'fidelity bar' as acceptance criteria (pixel-perfect not feasible for every visual) | Acceptance | Sharath | Jul 2026 | Open
Note: Progress is measured against Tableau's full feature surface and validated continuously on a reference workbook (21 worksheets), not tied to any one project. Honest caveat: parser EXTRACTION is ahead of end-to-end RENDER fidelity — some sheets parse completely but don't yet render, pending calculation-translation and multi-datasource work.