## Status Tracker
Tableau → Streamlit-in-Snowflake — Project Status Tracker
Update the % Complete, RAG and Notes each reporting cycle. Overall % and counts roll up automatically. Blue = you edit.
Reporting date | 2026-07-15 | Target | Oct 2026 | Owner | Sharath Kumar | Overall %
ID | Milestone | Owner | Start | Target | % Complete | RAG | Notes
M1 | Discovery & target architecture | Lead | Apr 2026 | May 2026 | 100% | G | Licenses, Snowflake+SiS architecture, compute sizing agreed.
M2 | Core accelerator engine (parse→translate→codegen→render) | Sharath | May 2026 | Jun 2026 | 100% | G | Generic pipeline works end-to-end; any workbook → multi-tab app.
M3 | Data layer in Snowflake | Data Eng | Jun 2026 | Aug 2026 | 85% | G | Local + full data wired (totals match). Snowflake mapping & 2nd source pending.
M4 | Dashboard fidelity — 6 dashboards matched | Sharath | Jun 2026 | Aug 2026 | 90% | G | 3 of 6 verified (Overview, Product, Customer).
M5 | Calculation translation incl. table calcs | Sharath | Jun 2026 | Aug 2026 | 97% | G | Core + LOD done; RANK/INDEX parsed; engine wiring + DATEDIFF pending.
M6 | Interactivity — filters, parameters, actions | TBD | Aug 2026 | Sep 2026 | 55% | A | Per-tab filters live; parameters/actions/tooltips pending.
M7 | Deployment to SiS (auth, refresh, RLS) | TBD | Sep 2026 | Oct 2026 | 80% | G | Not started; needs Snowflake account/roles decision.
M8 | Accelerator UI + QC report | TBD | Sep 2026 | Oct 2026 | 50% | A | QA harnesses built; UI + QC report pending.
Milestones complete (100%):
Completed this period |  |  |  |  | Planned next period
• Table-calc engine shipped (WINDOW_*/RANK/INDEX → SQL windows). |  |  |  |  | • Bins/histogram; context filters.
• Multi-table relationship extracts flatten automatically; E-Commerce 46→68%. |  |  |  |  | • Live-source semantic views in Snowflake.
• Top-N, hierarchies drill, device layouts, silent-gap findings shipped. |  |  |  |  | • Credentialed SiS deploy dry-run.
• Corpus grew to 7 workbooks (two official 2024.3 samples: 96%/100%). |  |  |  |  | • Edge-case workbook (joins/multi-fact/RLS).
• Regression suite now 13 gates; weekly report self-updating.
Risks & decisions needed
Item | Impact | Owner | Need by | Status
Multi-datasource & RLS need a Snowflake account + roles decision | Blocks M3/M7 | Director | Aug 2026 | Open
Complex visuals (Sankey/matrix/dual-axis): auto-convert vs flag in QC report? | Scope/timeline | Lead+Director | Jul 2026 | Open
Effectively 1 developer — timeline assumes added Data + App engineers | Timeline | Director | Jul 2026 | Open
Agree 'fidelity bar' as acceptance criteria (pixel-perfect not feasible for all) | Acceptance | Director | Jul 2026 | Open